## Sample DEC
[5 empty] | Duration |  | Month
[7 empty] | Development |  | Construction- |  |  | Construction
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1. Permitting & Regulatory Approvals |  |  |  |  | 5
| Construction permit |  | AAB | Jelmer | 5 | bar: Development 1 to Construction- 5
BESS permit | bar: Development 2 to Construction- 3
2. Procurement & Contracting |  |  |  |  | 9
| EPC selection |  | Jeroen | Jelmer | 2 | bar: Development 2
| MEP vendors |  | Jeroen | Jelmer | 2 | bar: Development 2
Long Load Items | bar: Construction- 3 to Construction 10
3. Bess development |  |  |  |  | 7
| Concrete + foundation |  | Civil contractor | Jelmer | 2 | bar: Construction 6 to Construction 7
| Transformer |  | E contractor | Jelmer | 1 | bar: Construction 7
| Supplier |  | BESS contractor | Jelmer | 1 | bar: Development 2
| Leat time |  | BESS contractor |  | 5 | bar: Construction- 4 to Construction 8
| Installation |  | BESS contractor | Jelmer | 1 | bar: Construction 9
4. Design & Engineering |  |  |  |  | 5
| Riba 2 |  | AAB | DJ | 2 | bar: Development 1 to Development 2
| Riba 3 | EPC | Design Contractor | DJ | 2 | bar: Construction- 3
| Riba 4 | EPC | Design Contractor | DJ | 4 | bar: Construction- 4 to Construction- 5
| design freeze |  |  | DJ/Jeroen | bar: Construction- 5
5. Control |  |  |  |  | 7
| EMS strategy |  |  | DJ | bar: Construction- 3 to Construction- 4
| EMS installation |  |  | DJ | bar: Construction 6 to Construction 7
| EMS testing |  |  | DJ | bar: Construction 8
| EMS Commissioning |  |  | DJ | bar: Construction 9
| BMS installation |  |  | DJ
| BMS testing |  |  | DJ
| BMS Commissioning |  |  | DJ
6. Construction (Shell & Core) |  |  |  |  | 5.5
| Concrete + foundation | EPC | Civil contractor | Jeroen | 2 | bar: Construction 6
| Shell + lights/doors/ | EPC | Civil contractor | Jeroen | 2 | bar: Construction 7 to Construction 8
| Transformers, UPS, Main distribution | EPC | E contractor | Jeroen | 1.5 |  | Construction 10: 1; Construction 11: 0.5
| Power cables & Main busbars | EPC | E contractor | Jeroen | 1.5 |  | Construction 10: 1; Construction 11: 0.5
| Heat pumps | EPC | W contractor | Jeroen | 2 | bar: Construction 10 to Construction 11
| water works | EPC | W contractor | Jeroen | 2 | bar: Construction 10 to Construction 11
7. Customer Fit-Out (White Space + MEP) |  |  |  |  | 1 | bar: Development 1 to Construction 13
| Whitespace fitout incl "Run" | EPC | Civil contractor | Jeroen | 0.5 |  | Construction 12: 0.5
| Distribution Busbar | EPC | E contractor | Jeroen | 1 | bar: Construction 12
| Air cooling | EPC | W contractor | Jeroen | 1 | bar: Construction 12
| Hot/Cold aisle if applicable | EPC | Civil contractor | Jeroen | 1 | bar: Construction 12
8. Commissioning & Testing |  |  |  |  | 1.5 | bar: Development 1 to Construction 13
| E testing | EPC | E contractor | Yoni? | 0.5 |  | Construction 13: 0.5
| W testing | EPC | W contractor | Yoni? | 0.5 |  | Construction 13: 0.5
| Load bank test | EPC | Ops Contractor | Yoni? | 0.5 |  | Construction 13: 0.5
9. Operations Onboarding |  |  |  |  | 4 | bar: Development 1 to Construction 14
| Standard operating procedures | EPC | Ops Contractor | Yoni? | 3 | bar: Construction 11 to Construction 13
| As build drawings | EPC | Design Contractor | DJ | 1 | bar: Construction 14
| Customer onboarding | Ops Contractor | Ops Contractor | Yoni? | 1 |  | Construction 13: 0.5
CAPEX | [6 empty] | 0 | 0 | 15.2502 | 0 | 0 | 12.6501 | 0 | 0 | 0 | 0 | 2.6 | 0
| Power distribution busbars (4 feeds) | 524001.7576 |  |  |  | 0.786 | Construction- 3: 50%; Construction 6: 40%; Construction 11: 10%
| EPC selection | 3000000 |  |  |  | 4.5 | Construction- 3: 50%; Construction 6: 50%
| Main distribution (UPS, LV switchgear, switchboards) | 5400000 |  |  |  | 8.1 | Construction- 3: 50%; Construction 6: 40%; Construction 11: 10%
| Heat-reuse HEX skid | 2000000 |  |  |  | 3 | Construction- 3: 50%; Construction 6: 40%; Construction 11: 10%
| BESS (battery energy storage system) |  | (already in BESS CAPEX) |  |  | 0 | Construction- 3: 90%; Construction 11: 10%
| Primary cooling loop (pumps, primary piping, plant controls) | 1000000 |  |  |  | 1.5 | Construction- 3: 50%; Construction 6: 40%; Construction 11: 10%
| Secondary cooling loop piping/pumps | 2000000 |  |  |  | 3 | Construction- 3: 50%; Construction 6: 40%; Construction 11: 10%
| Secondary cooling loop — Air (Rear-door, Fancoil ,AHUs, ducting) | 1296000 |  |  |  | 1.944 | Construction- 3: 50%; Construction 6: 40%; Construction 11: 10%
| Dry coolers | 317911 |  |  | 7.3333 | 0.47687 | Construction- 3: 50%; Construction 6: 40%; Construction 11: 10%
| Fire security | 555631.5789 |  |  | 7 | 0.83345 | Construction- 3: 50%; Construction 6: 40%; Construction 11: 10%
| Security systems (CCTV, access control, IDS) | 480000 |  |  |  | 0.72 | Construction- 3: 50%; Construction 6: 40%; Construction 11: 10%
| Certification (e.g., Uptime/Tier, ISO, commissioning cert fees) | 960000 |  |  |  | 1.44 | Construction- 3: 50%; Construction 6: 40%; Construction 11: 10%
| Commissioning (incl. test-runs) | 2000000 |  |  |  | 3 | Construction- 3: 50%; Construction 6: 40%; Construction 11: 10%
| Shell (building structure/envelope) | 800000 |  |  |  | 1.2 | Construction- 3: 50%; Construction 6: 40%; Construction 11: 10%
| Contingengy | 50% |  |  |  |  | Construction- 3: 50%; Construction 6: 40%; Construction 11: 10%
| Total |  |  |  |  | 30.5003
| E/MW |  |  |  |  | 7.6251
FTE EPC
Legal | 0.2 | EPC |  |  |  |  | Development 1: 0.2; Development 2: 0.2; Construction- 3: 0.2; Construction- 4: 0.2
PM/Construction Manager | 1 | EPC
PM | 1 | EPC
Quality Control | 1 | EPC
Procurement | 0.5 | EPC |  |  |  |  | Construction- 5: 0
FTE Non-EPC
Legal | 0.5 | Non EPC
Electrical Engineering | 1.5 | Non EPC
Construction Management | 1 | Non EPC
Water/MEP Systems | 1 | Non EPC
Project Management | 1 | Non EPC
Quality Control | 1 | Non EPC
Procurement | 1.2 | Non EPC
HSE | 1 | Non EPC
Security | 7 | Non EPC
Cost Control | 1 | Non EPC

## Sample BESS
|  |  |  | Duration | CAPEX | Month
[6 empty] | Growth |  |  | Development |  |  | Construction
[6 empty] | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6
2. Land & Grid Securing
| HoT |  | Co | 1 | bar: Growth 0
| Grid |  | Co | 2 | bar: Growth -2 to Growth -1
3. Permitting & Regulatory Approvals
| BESS permit |  | Jelmer | 6 | bar: Development 1 to Development 3
6A Bess development
| Concrete + foundation | BESS contractor | Jelmer | 2 | bar: Construction 4
| Transformer | BESS contractor | Jelmer | 1 | bar: Construction 5
| Supplier | BESS contractor | Jelmer | 1 | bar: Development 1
| Leat time |  |  | 5 | bar: Development 2 to Construction 6
| Installation | BESS contractor | Jelmer | 1 | bar: Construction 6
Control
| EMS strategy |  | DJ | bar: Development 3
| EMS installation |  | DJ | bar: Construction 6
| EMS testing |  | DJ | bar: Construction 6
| EMS Commissioning |  | DJ
CAPEX | [8 empty] | 2.2724 | 0 | 0 | 0 | 0 | 0.23916
| BESS (battery energy storage system) | 1992960 |  |  | 2.3916 | Development 1: 90%; Construction 6: 10%
| Concrete + foundation | 100000 |  |  | 0.12 | Development 1: 100%
| Contingency + Installation | 20%
| Total |  |  |  | 2.5116
| E/MW |  |  |  | 0.62789

## Planning 2026_2027
Year |  |  |  | Start month |  |  |  | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027
Month |  |  |  | D | C- | C | Done | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
| MW IT | Type |  | 1 | 3 | 6 | 14
DC 1 (Powergrow) | 4 | EPC |  | 1 | 3 | 6 | 14 | D | D | C- | C- | C- | C | C | C | C | C | C | C | C | C
DC 2 (EPFlora) | 4 | EPC |  | 1 | 5 | 10 | 20 | D | D | D | D | C- | C- | C- | C- | C- | C | C | C | C | C | C | C | C | C | C | C
DC 3 | 4 | non-EPC |  | 2 | 8 | 14 | 25 |  | D | D | D | D | D | D | C- | C- | C- | C- | C- | C- | C | C | C | C | C | C | C | C | C | C | C | C
DC 4 | 8 | EPC |  | 6 | 12 | 18 | 27 | [5 empty] | D | D | D | D | D | D | C- | C- | C- | C- | C- | C- | C | C | C | C | C | C | C | C | C | C
DC 5 | 8 | EPC |  | 6 | 12 | 18 | 27 | [5 empty] | D | D | D | D | D | D | C- | C- | C- | C- | C- | C- | C | C | C | C | C | C | C | C | C | C
MW Utility
BESS 1 | 5 |  | DC 1 | 2 | 5 | 5 | 7 |  | D | D | D | C | C | C
BESS 2 | 5 |  | DC 2 | 3 | 6 | 6 | 8 |  |  | D | D | D | C | C | C
BESS 3 | 5 |  | DC 3 | 5 | 8 | 8 | 10 |  |  |  |  | D | D | D | C | C | C
BESS 4 | 10 |  | DC 4 | 6 | 9 | 9 | 11 | [5 empty] | D | D | D | C | C | C
BESS 5 | 10 |  | DC 5 | 7 | 10 | 10 | 12 | [6 empty] | D | D | D | C | C | C
BESS 6 | 5 |  |  | 8 | 11 | 11 | 13 | [7 empty] | D | D | D | C | C | C
BESS 7 | 10 |  |  | 9 | 12 | 12 | 14 | [8 empty] | D | D | D | C | C | C
BESS 8 | 10 |  |  | 10 | 13 | 13 | 15 | [9 empty] | D | D | D | C | C | C
BESS 9 | 5 |  |  | 11 | 14 | 14 | 16 | [10 empty] | D | D | D | C | C | C
BESS 10 | 10 |  |  | 12 | 15 | 15 | 17 | [11 empty] | D | D | D | C | C | C
CAPEX | MW | Max (M€/MW) |  | Sum | (M€/MW)
DC 1 | 4 | 10 |  | 30.5003 | 7.6251 |  |  |  |  | 15.2502 |  |  | 12.6501 |  |  |  |  | 2.6 |  | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0
DC 2 | 4 | 9 |  | 30.5003 | 7.6251 | [6 empty] | 15.2502 |  |  |  |  | 12.6501 | [6 empty] | 2.6
DC 3 | 4 | 9 |  | 30.5003 | 7.6251 | [9 empty] | 15.2502 | [5 empty] | 12.6501 | [7 empty] | 2.6
DC 4 | 8 | 9 |  | 61.0006 | 7.6251 | [13 empty] | 30.5003 | [5 empty] | 25.3003 | [5 empty] | 5.2001
DC 5 | 8 | 9 |  | 61.0006 | 7.6251 | [13 empty] | 30.5003 | [5 empty] | 25.3003 | [5 empty] | 5.2001
BESS 1 | 5 | 0.2 |  | 2.5116 | 0.50231 |  |  |  | 2.2724 |  |  |  |  | 0.23916
BESS 2 | 5 | 0.2 |  | 2.5116 | 0.50231 |  |  |  |  | 2.2724 |  |  |  |  | 0.23916
BESS 3 | 5 | 0.2 |  | 2.5116 | 0.50231 | [6 empty] | 2.2724 |  |  |  |  | 0.23916
BESS 4 | 10 | 0.2 |  | 5.0231 | 0.50231 | [7 empty] | 4.5448 |  |  |  |  | 0.47831
BESS 5 | 10 | 0.2 |  | 5.0231 | 0.50231 | [8 empty] | 4.5448 |  |  |  |  | 0.47831
BESS 6 | 5 | 0.2 |  | 2.5116 | 0.50231 | [9 empty] | 2.2724 |  |  |  |  | 0.23916
BESS 7 | 10 | 0.2 |  | 5.0231 | 0.50231 | [10 empty] | 4.5448 |  |  |  |  | 0.47831
BESS 8 | 10 | 0.2 |  | 5.0231 | 0.50231 | [11 empty] | 4.5448 |  |  |  |  | 0.47831
BESS 9 | 5 | 0.2 |  | 2.5116 | 0.50231 | [12 empty] | 2.2724 |  |  |  |  | 0.23916
BESS 10 | 10 | 0.2 |  | 5.0231 | 0.50231 | [13 empty] | 4.5448 |  |  |  |  | 0.47831
Total DC | [7 empty] | 0 | 0 | 15.2502 | 0 | 15.2502 | 12.6501 | 0 | 15.2502 | 0 | 12.6501 | 2.6 | 61.0006 | 0 | 12.6501 | 0 | 0 | 2.6 | 50.6005 | 0 | 0 | 0 | 2.6 | 0 | 10.4001 | 0 | 0 | 0
Total BESS | [7 empty] | 0 | 2.2724 | 2.2724 | 0 | 2.2724 | 4.5448 | 4.7839 | 2.5116 | 4.5448 | 4.7839 | 2.7507 | 5.0231 | 0.23916 | 0.47831 | 0.47831 | 0.23916 | 0.47831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand total |  |  |  |  | M€ |  |  | 0 | 2.2724 | 17.5226 | 0 | 17.5226 | 17.1949 | 4.7839 | 17.7617 | 4.5448 | 17.4341 | 5.3507 | 66.0237 | 0.23916 | 13.1284 | 0.47831 | 0.23916 | 3.0783 | 50.6005 | 0 | 0 | 0 | 2.6 | 0 | 10.4001 | 0 | 0 | 0
FTE
FTE EPC
Active projects | [7 empty] | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Legal | 0.2 | [6 empty] | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
PM/Construction Manager | 1 | [6 empty] | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2
PM | 1 | [6 empty] | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Quality Control | 1 | [6 empty] | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Procurement | 0.5 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1
FTE Non-EPC
Active projects | [7 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Legal | 0.5 | [6 empty] | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
Electrical Engineering | 1.5 | [6 empty] | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0
Construction Management | 1 | [6 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Water/MEP Systems | 1 | [6 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Project Management | 1 | [6 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Quality Control | 1 | [6 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Procurement | 1.2 | [6 empty] | 0 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 0 | 0
HSE | 1 | [6 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Security | 7 | [6 empty] | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0
Cost Control | 1 | [6 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Total FTE |  | FTE Cost/M [k€]
Legal |  | 21 | [5 empty] | 0.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 0.4 | 0.4
Electrical Engineering |  | 23.1 | [5 empty] | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0
Construction Management |  | 25.2 | [5 empty] | 2 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 2 | 2
Water/MEP Systems |  | 23.1 | [5 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Project Management |  | 31.5 | [5 empty] | 2 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 2 | 2
Quality Control |  | 21 | [5 empty] | 2 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 2 | 2
Procurement |  | 18.9 | [5 empty] | 1 | 2.2 | 2.2 | 2.2 | 2.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 2.7 | 2.7 | 2.7 | 2.7 | 2.7 | 2.7 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 1 | 1
HSE |  | 16.8 | [5 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Security |  | 8.4 | [5 empty] | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0
Cost Control |  | 10.5 | [5 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Total Cost FTE |  | FTE Cost/M [k€]
Legal |  | 21 | [5 empty] | 8.4 | 29.4 | 29.4 | 29.4 | 29.4 | 37.8 | 37.8 | 37.8 | 37.8 | 37.8 | 37.8 | 37.8 | 37.8 | 37.8 | 33.6 | 33.6 | 33.6 | 33.6 | 33.6 | 33.6 | 29.4 | 29.4 | 29.4 | 29.4 | 29.4 | 8.4 | 8.4
Electrical Engineering |  | 23.1 | [5 empty] | 9.24 | 32.34 | 32.34 | 32.34 | 32.34 | 41.58 | 41.58 | 41.58 | 41.58 | 41.58 | 41.58 | 41.58 | 41.58 | 41.58 | 36.96 | 36.96 | 36.96 | 36.96 | 36.96 | 36.96 | 32.34 | 32.34 | 32.34 | 32.34 | 32.34 | 9.24 | 9.24
Construction Management |  | 25.2 | [5 empty] | 10.08 | 35.28 | 35.28 | 35.28 | 35.28 | 45.36 | 45.36 | 45.36 | 45.36 | 45.36 | 45.36 | 45.36 | 45.36 | 45.36 | 40.32 | 40.32 | 40.32 | 40.32 | 40.32 | 40.32 | 35.28 | 35.28 | 35.28 | 35.28 | 35.28 | 10.08 | 10.08
Water/MEP Systems |  | 23.1 | [5 empty] | 9.24 | 32.34 | 32.34 | 32.34 | 32.34 | 41.58 | 41.58 | 41.58 | 41.58 | 41.58 | 41.58 | 41.58 | 41.58 | 41.58 | 36.96 | 36.96 | 36.96 | 36.96 | 36.96 | 36.96 | 32.34 | 32.34 | 32.34 | 32.34 | 32.34 | 9.24 | 9.24
Project Management |  | 31.5 | [5 empty] | 12.6 | 44.1 | 44.1 | 44.1 | 44.1 | 56.7 | 56.7 | 56.7 | 56.7 | 56.7 | 56.7 | 56.7 | 56.7 | 56.7 | 50.4 | 50.4 | 50.4 | 50.4 | 50.4 | 50.4 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 12.6 | 12.6
Quality Control |  | 21 | [5 empty] | 8.4 | 29.4 | 29.4 | 29.4 | 29.4 | 37.8 | 37.8 | 37.8 | 37.8 | 37.8 | 37.8 | 37.8 | 37.8 | 37.8 | 33.6 | 33.6 | 33.6 | 33.6 | 33.6 | 33.6 | 29.4 | 29.4 | 29.4 | 29.4 | 29.4 | 8.4 | 8.4
Procurement |  | 18.9 | [5 empty] | 7.56 | 26.46 | 26.46 | 26.46 | 26.46 | 34.02 | 34.02 | 34.02 | 34.02 | 34.02 | 34.02 | 34.02 | 34.02 | 34.02 | 30.24 | 30.24 | 30.24 | 30.24 | 30.24 | 30.24 | 26.46 | 26.46 | 26.46 | 26.46 | 26.46 | 7.56 | 7.56
HSE |  | 16.8 | [5 empty] | 6.72 | 23.52 | 23.52 | 23.52 | 23.52 | 30.24 | 30.24 | 30.24 | 30.24 | 30.24 | 30.24 | 30.24 | 30.24 | 30.24 | 26.88 | 26.88 | 26.88 | 26.88 | 26.88 | 26.88 | 23.52 | 23.52 | 23.52 | 23.52 | 23.52 | 6.72 | 6.72
Security |  | 8.4 | [5 empty] | 3.36 | 11.76 | 11.76 | 11.76 | 11.76 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 13.44 | 13.44 | 13.44 | 13.44 | 13.44 | 13.44 | 11.76 | 11.76 | 11.76 | 11.76 | 11.76 | 3.36 | 3.36
Cost Control |  | 10.5 | [5 empty] | 4.2 | 14.7 | 14.7 | 14.7 | 14.7 | 18.9 | 18.9 | 18.9 | 18.9 | 18.9 | 18.9 | 18.9 | 18.9 | 18.9 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 14.7 | 14.7 | 14.7 | 14.7 | 14.7 | 4.2 | 4.2
Proje
Total FTE Cost |  | [M€] |  | 7.9002 | 0.28215 |  |  | 0.0798 | 0.2793 | 0.2793 | 0.2793 | 0.2793 | 0.3591 | 0.3591 | 0.3591 | 0.3591 | 0.3591 | 0.3591 | 0.3591 | 0.3591 | 0.3591 | 0.3192 | 0.3192 | 0.3192 | 0.3192 | 0.3192 | 0.3192 | 0.2793 | 0.2793 | 0.2793 | 0.2793 | 0.2793 | 0.0798 | 0.0798
|  |  |  | TOTAL FTE | Per MW
Capital Requirements |  |  |  | 259.0757 | 9.2527 |  |  | 0.0798 | 2.5517 | 17.8019 | 0.2793 | 17.8019 | 17.554 | 5.143 | 18.1208 | 4.9039 | 17.7932 | 5.7098 | 66.3828 | 0.59826 | 13.4875 | 0.79751 | 0.55836 | 3.3975 | 50.9197 | 0.3192 | 0.3192 | 0.2793 | 2.8793 | 0.2793 | 10.6794 | 0.2793 | 0.0798 | 0.0798
|  |  |  | TOTAL CAPEX | IT + BESS

## Sample EPC Resources
EPC Project Staffing Requirements
With EPC contractor handling main execution, your team provides oversight and coordination
Role | FTE Required | Responsibilities
Legal | 0.2 | Contract review, compliance oversight, permit coordination
Electrical Engineering | 0.3 | Design review, EPC coordination, testing oversight
Construction Management | 0.3 | Site visits, progress monitoring, EPC liaison
Water/MEP Systems | 0.2 | Cooling system review, water management oversight
Planning & Coordination | 0.4 | Schedule tracking, milestone monitoring, stakeholder updates
Quality Control | 0.3 | Inspection oversight, quality standards verification
Procurement | 0.2 | Long-lead item tracking, vendor coordination
Total | 1.9
Role | FTE Required | Responsibilities | NOTE
Legal | 0.2 | Contract review, compliance oversight, permit coordination
PM/Construction Manager | 1 | Site visits, progress monitoring, EPC liaison
PM | 1 | Schedule tracking, milestone monitoring, stakeholder updates
Quality Control | 1 | Inspection oversight, quality standards verification
Procurement | 0.5 | Long-lead item tracking, vendor coordination
Total | 3.7
ONE TIME
COORDINATION = PM, TEST = QC, Design = PROGRAM MANAGER
PM / CONSTRUCTION MANAGER

## Sample Non EPC Resources
Self-Managed Project Staffing Requirements
Full internal execution requiring comprehensive team across all disciplines
Role | FTE Required | Responsibilities
Legal | 0.5 | Contract negotiation, permitting, regulatory compliance, vendor agreements
Electrical Engineering | 1.5 | Full design, power distribution, backup systems, testing & commissioning
Construction Management | 2 | On-site supervision, contractor management, safety, schedule execution
Water/MEP Systems | 1 | Cooling design, water treatment, HVAC systems, mechanical coordination
Planning & Coordination | 1 | Master scheduling, resource allocation, critical path management
Quality Control | 1 | Full inspection program, testing, documentation, standards enforcement
Procurement | 1.2 | Vendor selection, negotiation, logistics, material tracking, cost control
Total | 8.2
|  |  | Daily rate (external hire) per person | Cost/day
Role | FTE Required | Responsibilities
Legal | 0.5 | Contract negotiation, permitting, regulatory compliance, vendor agreements | 1000 | 500 | 10500 | 21000
Electrical Engineering | 1.5 | Full design, power distribution, backup systems, testing & commissioning | 1100 | 1650 | 34650 | 23100
Construction Management | 1 | On-site supervision, contractor management, safety, schedule execution | 1200 | 1200 | 25200 | 25200
Water/MEP Systems | 1 | Cooling design, water treatment, HVAC systems, mechanical coordination | 1100 | 1100 | 23100 | 23100
Project Management | 1 | Master scheduling, resource allocation, critical path management | 1500 | 1500 | 31500 | 31500
Quality Control | 1 | Full inspection program, testing, documentation, standards enforcement | 1000 | 1000 | 21000 | 21000
Procurement | 1.2 | Vendor selection, negotiation, logistics, material tracking, cost control | 900 | 1080 | 22680 | 18900
HSE | 1 | Health and Safety Manager | 800 | 800 | 16800 | 16800
Security | 7 | During construction | 400 | 2800 | 58800 | 8400
Cost Control | 1 | Cost Control / adminstrative tasks | 500 | 500 | 10500 | 10500
254730
Total | 16.2 |  |  |  | 3056760